## Slide 1: Project Scheduling
COMP6100001 - Software engineering
Session 13
Kenny Jingga, S.Kom., M.T.

## Slide 2: Session 13 – Project Scheduling
Learning objectives
At the end of this session, students will be expected to be able to:
Understand the Importance of Project Scheduling in Software Engineering
Learn Techniques for Developing Project Schedules
Apply the Critical Path Method (CPM) and Other Scheduling Techniques

## Slide 3: Session 13 – Project scheduling
Content outline
Introduction to Project Scheduling
Developing Project Schedules
Critical Path Method (CPM)
Advanced Scheduling Techniques
Tools for Project Scheduling

## Slide 4: Introduction to Project Scheduling

## Slide 5: Introduction to Project Scheduling
Importance of Scheduling in Software Projects
Defines the Timeline: Establishes when tasks and milestones need to be completed.
Resource Planning: Helps allocate resources effectively over time.
Risk Mitigation: Identifies potential bottlenecks and allows for contingency planning.
Stakeholder Communication: Provides a visual representation of the project's progress.

## Slide 6: Introduction to Project Scheduling
Overview of Scheduling techniques
Traditional Scheduling Methods: Gantt Charts, PERT, and CPM.
Agile Scheduling Approaches: Iterative development, Scrum sprints.
Hybrid Methods: Combining traditional and agile techniques.

## Slide 7: Developing project Schedules
Gantt Charts: Components and interpretation
Tasks/Activities: Work items to be completed.
Timeline: Dates or time periods over which tasks occur.
Bars: Visual representation of task durations.
Dependencies: Relationships between tasks (may be shown with arrows or connectors).
Milestones: Significant points or events in the project.

## Slide 8: Developing project Schedules
Gantt Charts: Creating Gantt Charts
Identify Tasks: Break down the project into manageable activities.
Estimate Durations: Assign time estimates to each task.
Define Dependencies: Determine task sequences and relationships.
Construct the Chart: Use software tools or manually draw the chart.
Update Regularly: Reflect changes in the project schedule.

## Slide 9: Developing project Schedules
Gantt Charts: Advantages and Limitations
Advantages:
  Easy to understand and communicate.
  Visually depicts the project timeline.
  Helps track progress against planned activities.
Limitations:
  Can become complex for large projects.
  Does not explicitly show task dependencies unless enhanced.
  Static representation; may not adapt well to changes.

## Slide 10: Developing project Schedules
PERT (Program Evaluation Review Technique) Charts: Components And Interpretation
Nodes (Events): Represent milestones or the start/end of activities.
Arrows (Activities): Represent tasks; arrows connect nodes.
Dependencies: The sequence in which tasks must be performed.

## Slide 11: Developing project Schedules
PERT (Program Evaluation Review Technique) Charts: Constructing Pert Diagrams
List Activities: Include all tasks required for project completion.
Determine Dependencies: Identify which tasks depend on others.
Estimate Durations: Use optimistic, pessimistic, and most likely estimates if desired.
Draw the Network Diagram: Represent tasks and dependencies visually.

## Slide 12: Developing project Schedules
PERT (Program Evaluation Review Technique) Charts: Advantages and Limitations
Advantages:
  Clearly shows task dependencies.
  Helps identify the critical path.
  Useful for projects with uncertain activity durations.
Limitations:
  Can be complex to create and interpret.
  Requires accurate estimation of task durations.
  Not as visually intuitive as Gantt charts for some stakeholders.

## Slide 13: Critical Path Method (CPM)
Definition and Purpose
Definition:
  CPM is a step-by-step methodology used to identify critical and non-critical tasks with the goal of preventing time-frame problems and process bottlenecks.
Purpose:
  Determine the longest stretch of dependent activities.
  Calculate the shortest possible project duration.
  Identify tasks that have flexibility (float) and those that do not.

## Slide 14: Critical Path Method (CPM)
Steps to Determine the Critical Path
List All Activities: Breakdown the project into individual tasks.
Identify Dependencies: Understand the sequence of tasks.
Estimate Activity Durations: Assign realistic time estimates.
Create the Network Diagram: Visualize tasks and dependencies.
Calculate Earliest Start (ES) and Earliest Finish (EF) Times: Using forward pass.
Calculate Latest Start (LS) and Latest Finish (LF) Times: Using backward pass.
Determine Float (Slack) Times: Calculate for each activity.
Identify Critical Path: The path with zero total float.

## Slide 15: Critical Path Method (CPM)
Forward and Backward Pass Calculations
Forward Pass (Earliest Times)
Earliest Start (ES): The earliest time an activity can begin.
  ES for starting activities: Zero.
  ES for subsequent activities: ES = Maximum EF of all immediate predecessors.
Earliest Finish (EF): EF = ES + Activity Duration.
Backward Pass (Latest Times)
Latest Finish (LF): The latest time an activity can finish without delaying the project.
  LF for ending activities: Equal to the project's earliest finish time.
  LF for preceding activities: LF = Minimum LS of all immediate successors.
Latest Start (LS): LS = LF - Activity Duration.

## Slide 16: Critical Path Method (CPM)
Float (Slack) Time Analysis
Total Float: The amount of time an activity can be delayed without affecting the project's end date.
  Total Float = LS - ES or Total Float = LF - EF.
Free Float: Time an activity can be delayed without affecting the ES of subsequent activities.
Zero Float: Indicates activities on the critical path.

## Slide 17: Critical Path Method (CPM)
Example
Project: Developing a New Mobile Application.
Activities, Durations, and Dependencies:
Activity | Description | Duration (Days) | Predecessors
A | Requirements Gathering | 4 | -
B | UI Design | 3 | A
C | Backend Design | 5 | A
D | Frontend Development | 6 | B
E | Backend Development | 8 | C
F | Integration | 2 | D, E
G | Testing | 4 | F
H | Deployment | 1 | G

## Slide 18: Critical Path Method (CPM)
Example
Task:
  Construct the network diagram
  Perform forward and backward pass calculations
  Determine ES, EF, LS, LF, and float for each activity
  Identify the critical path

## Slide 19: Critical Path Method (CPM)
Example: Create Network Diagram
Task:
  Construct the network diagram
  Perform forward and backward pass calculations
  Determine ES, EF, LS, LF, and float for each activity
  Identify the critical path

## Slide 20: Critical Path Method (CPM)
Example: Perform Forward Pass
Activity A:
  ES = 0
  EF = ES + Duration = 0 + 4 = 4
Activity B:
  ES = EF of A = 4
  EF = 4 + 3 = 7
Activity C:
  ES = EF of A = 4
  EF = 4 + 5 = 9
Activity D:
  ES = EF of B = 7
  EF = 7 + 6 = 13
Activity E:
  ES = EF of C = 9
  EF = 9 + 8 = 17
Activity F:
  ES = Max(EF of D, EF of E) = Max(13, 17) = 17
  EF = 17 + 2 = 19
Activity G:
  ES = EF of F = 19
  EF = 19 + 4 = 23
Activity H:
  ES = EF of G = 23
  EF = 23 + 1 = 24

## Slide 21: Critical Path Method (CPM)
Example: Perform Backward Pass
Activity H:
  LF = Project EF = 24
  LS = LF - Duration = 24 - 1 = 23
Activity G:
  LF = LS of H = 23
  LS = LF - Duration = 23 - 4 = 19
Activity F:
  LF = LS of G = 19
  LS = LF - Duration = 19 - 2 = 17
Activity D:
  LF = LS of F = 17
  LS = LF - Duration = 17 - 6 = 11
Activity E:
  LF = LS of F = 17
  LS = LF - Duration = 17 - 8 = 9
Activity B:
  LF = LS of D = 11
  LS = LF - Duration = 11 - 3 = 8
Activity C:
  LF = LS of E = 9
  LS = LF - Duration = 9 - 5 = 4
Activity A:
  LF = Min(LS of B, LS of C) = Min(8, 4) = 4
  LS = LF - Duration = 4 - 4 = 0

## Slide 22: Critical Path Method (CPM)
Example: Calculate float for each activity
Activity A:
  Total Float = LS - ES = 0 - 0 = 0
Activity B:
  Total Float = 8 - 4 = 4
Activity C:
  Total Float = 4 - 4 = 0
Activity D:
  Total Float = 11 - 7 = 4
Activity E:
  Total Float = 9 - 9 = 0
Activity F:
  Total Float = 17 - 17 = 0
Activity G
  :Total Float = 19 - 19 = 0
Activity H:
  Total Float = 23 - 23 = 0

## Slide 23: Critical Path Method (CPM)
Example: Identify Critical Path
Activities with zero total float: A → C → E → F → G → H
Critical Path: A-C-E-F-G-H
Project Duration: 24 days

## Slide 24: Advanced ScheduLing Techniques
Agile and Iterative Scheduling
Timeboxing: Allocating a fixed time period for each process.
Sprints: Short, consistent durations (e.g., 2 weeks) where specific work is completed.
Backlogs and Burn-down Charts: Tools to manage and visualize progress.

## Slide 25: Advanced ScheduLing Techniques
Timeboxing and Sprint Planning
Timeboxing Benefits:
  Encourages focus on priorities.
  Improves predictability and efficiency.
  Facilitates regular delivery of increments.
Sprint Planning:
  Define sprint goals.
  Select backlog items to include.
  Estimate tasks and assign responsibilities.

## Slide 26: Advanced ScheduLing Techniques
Resource-Constrained Scheduling
Definition: Adjusting the schedule based on resource availability.
Techniques:
  Resource Leveling: Modifying task schedules to minimize resource peaks and valleys.
  Resource Allocation Heuristics: Prioritizing tasks based on criticality and resource demands.

## Slide 27: Advanced ScheduLing Techniques
Fast Tracking and Crashing Techniques
Fast Tracking:
  Performing tasks in parallel that were originally planned in sequence.
  Risks: Increased complexity, potential for rework.
Crashing:
  Adding resources to critical path tasks to shorten durations.
  Considerations: Diminishing returns, increased costs.

## Slide 28: Tools for Project Scheduling
Software Tools
Microsoft Project:
  Comprehensive project management tool.
  Features: Gantt charts, resource management, reporting.
Jira:
  Focused on agile project management.
  Features: Backlogs, sprint planning, issue tracking.
Asana:
  Flexible project management platform.
  Features: Task lists, timelines, collaboration tools.

## Slide 29: Tools for Project Scheduling
Best Practices for using scheduling tools
Regular Updates: Keep schedules current to reflect actual progress.
Collaboration: Use tools that support team communication and collaboration.
Training: Ensure team members are proficient with the selected tools.
Customization: Tailor tools to fit the project's specific needs.

## Slide 30: References
Titus Winters, Tom Manshreck, and Hyrum Wright. (2020). Software Engineering at Google: Lesson Learned from Programming Over Time. 1st. O’Reilly Media. California. ISBN: 978-1492082798. Page 69-122.
Roger Pressman and Bruce Maxim. (2020). Software Engineering: A Practitioner's Approach. 9th. McGraw Hill. New York. ISBN: 978-1259872976. Chapter 24.
Ian Sommerville. (2016). Software Engineering. 10th. Pearson. London. ISBN: 978-1-292-09613-1. Chapter 22.
Project Management Institute. (2021). A Guide to the Project Management Body of Knowledge (PMBOK Guide) (7th Edition). Project Management Institute